## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
The core "Filesystem-only" scanning engine was successfully implemented and validated as secure. | Initial OS detection still relies on docker run, which partially bypasses the "no execution" goal. | Integrate with live CVE feeds (e.g., OSV.dev or NVD API) to move beyond a demo dataset. | Research and implement an API client for OSV.dev in the next sprint. | Example
Supported multiple OS distributions (Alpine/Debian) through a flexible modular architecture. | The local vulnerability dataset (demo_cves.json) is too small for production use cases. | Support application dependency scanning (e.g., parsing requirements.txt or package.json). | Schedule a design spike to explore parsing app-level lockfiles within the exported tarball.
Automated reporting (JSON/Markdown) was delivered on time and provides actionable feedback. | Documentation was initially deprioritized, leading to a large effort required at the end of the sprint. | Explore non-exec OS detection methods (e.g., checking layers/metadata via docker inspect). | Refactor the OSDetector to use docker inspect as the primary detection mechanism.
Successfully implemented complex version range comparison logic for accurate CVE matching. | Performance issues (timeouts) were observed when exporting very large container images. | Implement a caching layer for frequently scanned images or package databases. | Set up a performance benchmarking suite to identify bottlenecks in the export/extraction process.